## Slide 1
NT
NUTRITRACK
v0.1.0 · build 2026.07.08
STATUS REPORT
Platform, infrastructure,
architecture & UX
Top-priority problem list with risk & urgency
REPORT DATE
2026-07-08 · 00:12 Asia/Shanghai
AUTHOR
Mavis (audit + analysis)

## Slide 2
SECTION 01
Executive Summary
Where NutriTrack stands today, in 4 numbers
30%
Production-ready
Code is structured
but doesn't build
9,373
Dart LOC
across 6 features,
clean architecture
31
Compile errors
block next build,
all in 2 files
0
Tests
zero coverage,
test/ doesn't exist
WHAT'S WORKING
✓ AI gateway architecture
✓ Drift DB schema (7 tables)
✓ PB live (8 nt_* collections)
✓ Brand identity shipped
✓ AI vision + offline cache
HALF-BUILT
⚠ 5/6 screens render fake data
⚠ No auth / onboarding route
⚠ Workout session UI missing
⚠ Exercise DB: 46/488 (9.4%)
⚠ No Sentry / crash reporting
BLOCKERS
✗ App won't compile
✗ Never run on a device
✗ 9 packages on major N-1
✗ No crash reporting
✗ 7 dead dependencies
NutriTrack · Status Report · 2026-07-08
2 / 14

## Slide 3
SECTION 02
Platform Status
Flutter SDK, dependencies, platform readiness
STACK SNAPSHOT
Flutter
3.27+ (declared) · 3.29.3 in your lockfile
✓
Dart
3.6+ · supports records, patterns, sealed
✓
State
Riverpod 2.6.1 with @riverpod codegen
✓
Routing
go_router 14.8.1 (StatefulShellRoute)
✓
Local DB
Drift 2.28.2 (7 tables, all defined)
✓
AI Gateway
OpenRouter → MiniMax M3 + Gemini + GPT-4o
✓
Voice
record 5.1.2 → Whisper transcription
✓
Barcode
mobile_scanner 5.2.3 + OFF client
⚠
Camera
camera 0.11.4 → 0.12.0+1 available
⚠
Cloud sync
Supabase declared but unused
⚠
Health
REMOVED in this sprint (incompat)
✗
BUILD READINESS
Android compile
✗ FAILS
31 errors in barcode/camera
Android (post-fix)
STAGING
~45 min of mechanical fixes
iOS compile
UNKNOWN
macOS runner; not validated
Device run
NEVER
No `flutter run` ever executed
flutter analyze
31 errors + 17 warnings + 62 info
in 6 files
dart fix --apply
WOULD KILL 12 of 17 warnings
5 sec cleanup
pubspec.lock
GITIGNORED
fresh clone = `pub get`
Generated files
GITIGNORED
fresh clone = `build_runner`
Secrets config
TEMPLATE ONLY
user must cp template
NutriTrack · Status Report · 2026-07-08
3 / 14

## Slide 4
SECTION 03
Infrastructure Status
PocketBase, GitHub Actions, dependencies
POCKETBASE · LIVE SCHEMA
9 collections on pocketbase.scaleupcrm.com
nt_users
0 records
auth-anchored profiles
nt_food_logs
0 records
synced meal entries
nt_exercises
46 records
chest-only seeded
nt_workout_sessions
0 records
session history
nt_weight_entries
0 records
weight log
nt_favorites
0 records
starred foods
nt_meal_templates
0 records
recurring meals
nt_sync_queue
0 records
offline→cloud queue
nt_barcode_cache
0 records
OFF cache (anon read)
GITHUB ACTIONS · CI/CD
3 workflows + 1 README
ci.yml
ubuntu/macos runners · analyze + test + build APK/iOS
off-to-pb-sync.yml
cron 0 */6h · fetches OFF products → PB cache
dependency-sync.yml
weekly · opens PR for outdated packages
SECRETS
PB_URL
in workflow env
PB_ADMIN_EMAIL
in workflow secrets
PB_ADMIN_PASSWORD
in workflow secrets
OPENROUTER_API_KEY
in secrets.dart (template only)
NutriTrack · Status Report · 2026-07-08
4 / 14

## Slide 5
SECTION 04
Architecture
Domain-Driven Design · 6 features · 7 Drift tables
FEATURES BY SIZE
camera
snap → AI → review
1962
dashboard
today's meals + macros
1969
barcode
scan → OFF lookup
1654
workout
search + log
1046
settings
TDEE + profile
736
insights
weight + trends
481
DRIFT TABLES (7)
FoodLogEntries
meal entries + macros + source
ExerciseEntries
logged exercises per session
WorkoutSessions
active + history sessions
WeightEntries
weight log + date
UserProfiles
TDEE + goal + biometrics
ImageHashCache
AI dedup (avoid re-recognize)
PendingSyncEntries
offline → cloud queue
DATA FLOW
Capture → AI Gateway → Drift (local) → PocketBase (cloud) · 3-tier barcode cache: in-memory → PB → OFF (anonymous read)
NutriTrack · Status Report · 2026-07-08
5 / 14

## Slide 6
SECTION 05
Current Task Status
What's done, what's in progress, what's blocked
DONE
12
✓
Drift migration (Isar removed)
✓
PB schema live (9 collections)
✓
46 chest exercises seeded
✓
AI gateway architecture
✓
Drift codegen working
✓
Brand identity (icon, palette)
✓
Brand exports (iOS/Android/Web)
✓
KNOWN_WARNINGS.md written
✓
Gradle 8.14.0 + AGP 8.11.1
✓
record 5.1.2 pin (Linux iface)
✓
health plugin removed
✓
media/ golden-source structure
IN PROGRESS
3
⟳
Audit doc v2 (PRODUCTION_READINESS)
⟳
Strategy doc (WHAT_MISSING)
⟳
Major-version debt tracking (§6)
BLOCKED
5
✗
Android compile
31 errors in 2 files
✗
First device run
no working APK/IPA
✗
Insights screen
renders fake sample data
✗
Workout session UI
no active-session flow
✗
Onboarding flow
no /onboarding route
VELOCITY
9 commits in last 7 days · ~3 commits/day · clear blockers to unblock more
NutriTrack · Status Report · 2026-07-08
6 / 14

## Slide 7
SECTION 06
UX Status
What users would see today if the app compiled
SCREENS
6
dashboard, workout,
insights, settings,
camera, barcode
WIRED TO DATA
1 of 6
5 of 6 screens render
placeholder / sample data
EMPTY STATES
0
no `shimmer`, no
empty-state illustrations
MOTION + HAPTIC
minimal
app_motion exists
but underused
SCREEN-BY-SCREEN UX READINESS
Dashboard
✓ real data wiring
✗ fake data, no onboarding
Workout
✓ search working
✗ no session UI, no rest timer
Insights
✓ fl_chart present
✗ renders `_generateSampleWeights()`
Settings
✓ TDEE wizard OK
✗ no first-launch gate
Camera
✓ build broken
✗ 31 compile errors
Barcode
✓ build broken
✗ RRect.topLeft undefined
NutriTrack · Status Report · 2026-07-08
7 / 14

## Slide 8
SECTION 07
Performance Suggestions
What to fix before users notice the lag
1
Skeleton loaders on every list
Dashboard tiles, exercise search, history, insights charts all flash empty→full. Add shimmer widgets.
~4 hours
BIG
2
RepaintBoundary around MacroDonut
Already added in earlier commit. Verify on real device — fl_chart redraws on every frame otherwise.
~1 hour
MED
3
Cache Network images (cached_network_image)
Barcode images already wrapped. Apply same pattern to food images from OFF / PB.
~2 hours
MED
4
Lazy-load PB collections
Currently FoodLogRepository fetches full day on every screen mount. Use Drift streams (watchByDate) instead of getByDate.
~3 hours
BIG
5
Profile-mode build for production
flutter build apk --release --obfuscate --split-debug-info=debug/. Cuts ~30% APK size.
~30 min
QUICK
6
Image compression before AI
Camera capture = 2-4 MB JPEG. Resize to 1024px, JPEG quality 85 = ~200 KB. Faster AI upload, lower bandwidth.
~2 hours
MED
7
Skia caching for static content
macro_donut, wordmark, empty states — wrap in RepaintBoundary or const where possible.
~2 hours
MED
8
Sync TextEditingController (already done)
Workout search field — verify no sync creation in build(). You fixed this already. ✓
✓
DONE
NutriTrack · Status Report · 2026-07-08
8 / 14

## Slide 9
SECTION 08
Security Suggestions
What to lock down before the first user logs in
API keys not in code
OK
OpenRouter key in secrets.dart (template-only today). Never committed.
Secrets.dart in .gitignore
OK
.gitignore line 47: lib/core/config/secrets.dart. Verified.
PB admin creds in CI
OK
GitHub Actions secrets only. Not in any yml file. Verified.
Barcode cache: anonymous read
OK
PB listRule='' → world-readable. Only OFF data, no PII.
Crash reporting
MISSING
No Sentry, no Crashlytics. PII may end up in error logs unfiltered.
TLS pinning
MISSING
Dio talks to PB and OpenRouter over HTTPS, but cert pinning not configured. Acceptable for v1; revisit for v2.
Image storage on device
PARTIAL
Camera captures go to app-private dir (good). But they're never deleted; could leak via forensic tools.
PII in error logs
RISK
AppErrorHandler captures PlatformDispatcher.onError — should redact email, weight, food names before logging.
Supabase auth
MISSING
Auth is currently local-only. Once you re-add Supabase, must configure RLS on every table from day 1.
Dependency CVE scan
MISSING
No automated npm/advisory scan. GitHub Dependabot could enable in 5 minutes.
ProGuard / R8 obfuscation
ENABLED
android/app/build.gradle: minifyEnabled true, shrinkResources true. ✓
Debug signing for release
RISK
build.gradle uses the debug keystore for release builds. Acceptable for early access; MUST replace before public launch.
NutriTrack · Status Report · 2026-07-08
9 / 14

## Slide 10
SECTION 09
UX Suggestions
What separates "functional app" from "delightful app"
Onboarding
MISSING
3-screen first-run: welcome → why-we're-different → TDEE wizard. Without it users churn in 30s.
2 days
CRITICAL
Empty states
MISSING
Every screen needs a 'nothing here yet' moment with personality + a CTA. 8 illustrations needed.
1 day
HIGH
Haptic feedback
PARTIAL
HapticFeedback.mediumImpact on meal log, workout complete, set save. iOS-native feel.
2 hours
MED
Sound design
MISSING
Swoosh on log, bell on workout complete. just_audio already in pubspec, just unused.
4 hours
MED
Streaks + badges
MISSING
5-day logging streak, 7-day protein goal hit. Duolingo's #1 retention mechanism. Pure motivation.
3 days
HIGH
Pull-to-refresh
MISSING
Dashboard re-aggregates. Insights re-queries. Standard mobile pattern.
2 hours
LOW
Quick actions
MISSING
Long-press dashboard tile → quick log. Swipe-to-delete meal. iOS share extension later.
1 day
MED
Offline indicator
MISSING
Banner: 'Offline — logging locally, will sync when reconnected' + queue count.
3 hours
MED
Wow moment
MISSING
First time user logs via voice or camera → confetti + 'Saved 2 minutes vs typing!'
3 hours
HIGH
Error messages
PARTIAL
AppErrorHandler exists but messages should be human, specific, actionable.
1 day
MED
a11y
MISSING
No Semantics audit, no contrast check, no dynamic font scaling tested.
2 days
MED
i18n
MISSING
English-only is fine for v1, but structure (.arb) must support it. ~150 strings to externalize.
2-3 days
LOW
NutriTrack · Status Report · 2026-07-08
10 / 14

## Slide 11
SECTION 10
Top Problems · Critical · Act NOW
Blockers that prevent any further work
01
Build is broken — 31 compile errors
WHERE: lib/features/barcode/presentation/screens/barcode_scanner_screen.dart (27 errors) + lib/features/camera/presentation/screens/camera_screen.dart (4 errors)
WHAT: RRect.topLeft/topRight/bottomLeft/bottomRight undefined (use Rect or RRect.tlRadius). 3 callbacks with `Function()` instead of `Function(String)`. MobileScannerErrorBuilder API drift.
IMPACT: App won't run on any device. Nothing else matters until this is fixed.
EFFORT
45 min
TASK #1: Mechanical patch
02
Zero tests, no test/ directory
WHERE: No unit tests, no widget tests, no integration tests.
WHAT: flutter test --coverage in CI passes only because there are no tests to fail. Every future refactor is a coin flip.
IMPACT: Regressions slip through silently. New contributors can't find patterns to copy.
EFFORT
1-2 days
TASK #5 in roadmap
03
No onboarding, no first-run experience
WHERE: Initial route is /dashboard. No /login, /signup, or /onboarding route exists.
WHAT: User opens the app, sees generic 2000 kcal target with no context. Churns in 30 seconds.
IMPACT: Without onboarding, retention is impossible to measure or improve.
EFFORT
2 days
TASK #6 in roadmap
04
All data wiring is fake / sample
WHERE: Insights screen renders `_generateSampleWeights()`. Workout screen has no session UI. Dashboard donut takes fake numbers. Camera/barcode review sheets show static UI.
WHAT: 5 of 6 main screens are basically tech demos. Drift tables exist but are unused.
IMPACT: Without real data, the app cannot ship. No amount of polish hides this.
EFFORT
4 days
TASK #7 in roadmap
NutriTrack · Status Report · 2026-07-08
11 / 14

## Slide 12
SECTION 11
Top Problems · High Priority · This Week
After the critical path, address these
05
No crash reporting (Sentry/Crashlytics)
No sentry_flutter, no firebase_crashlytics dep. AppErrorHandler captures errors but doesn't report them anywhere.
IMPACT: Production without crash reporting = blind. You can't fix bugs you don't know about. PII risk if errors aren't redacted before logging.
EFFORT
2 hours
FIX
Add sentry_flutter, wrap AppErrorHandler
06
Voice logging UI half-built
record: ^5.1.2 + Whisper path defined in AI gateway. Quick log bar has a mic icon. But no hold-to-talk button, no waveform animation, no transcription feedback.
IMPACT: This is NutriTrack's #1 differentiator vs MyFitnessPal. Without it, app is just another calorie tracker.
EFFORT
3 days
FIX
Hold-to-talk + waveform + Whisper wiring
07
AI camera lacks verification flow
Camera captures, AI returns FoodLogEntry list with confidence. But no UI to show confidence bars or ask user to confirm low-confidence items.
IMPACT: Without verification, users lose trust the moment AI guesses wrong. Need red/yellow/green confidence indicator + 'Take another photo?' escape hatch.
EFFORT
3 days
FIX
Add confidence UI + quick-fix shortcuts
08
Exercise DB: 46 of 488
scripts/exercises_chest.js is the only seed file. Back/shoulders/arms/legs/glutes/core/cardio/full-body missing.
IMPACT: Workout feature is half-built. User can search but most muscle groups show zero results.
EFFORT
4-6 hours
FIX
Boilerplate: 8 more .js files
09
Workout session UI missing
WorkoutScreen has search + list. But no start session → log sets → rest timer → end session flow. No active-session screen, no PR tracking.
IMPACT: Half of NutriTrack's value prop is the workout side. Without session UI, it's a search tool, not a tracker.
EFFORT
4 days
FIX
Active session + set logger + rest timer
NutriTrack · Status Report · 2026-07-08
12 / 14

## Slide 13
SECTION 12
Top Problems · Medium Priority · This Month
Polish, performance, security hardening
10
9 packages on major N-1
flutter_riverpod 2.6 (latest 3.3), freezed 2.5 (3.2), mobile_scanner 5.2 (7.2), health REMOVED, go_router 14.8 (17.3), intl 0.19 (0.20), etc.
IMPACT: Future Flutter versions break these. Each is a real migration: API renames, codegen output changes, permission flow drift.
EFFORT
1 week
FIX
5 grouped PRs per KNOWN_WARNINGS §6
11
7 dead dependencies in pubspec
just_audio, web_socket_channel, confetti, flutter_staggered_animations, animations, lottie, gap, shimmer, supabase_flutter.
IMPACT: 0 imports in lib/ for most. ~10 MB wasted APK size. Slower builds.
EFFORT
30 min
FIX
flutter pub remove for each
12
README lies about Isar
Stack table says Local DB | Isar 3.1. You migrated to Drift 5 commits ago.
IMPACT: Confuses every new contributor. Costs an hour of confusion per onboarding.
EFFORT
10 min
FIX
3-line edit + bump version
13
Release build uses debug keystore
android/app/build.gradle: signingConfigs.release = signingConfigs.debug
IMPACT: Acceptable for internal testing. CRITICAL to replace before public launch — Play Store / App Store will reject.
EFFORT
1 hour
FIX
Generate release keystore, store in key.properties
14
Adaptive TDEE engine not built
TDEE wizard calculates starting value. But no weekly recalibration from real weight + intake data.
IMPACT: MacroFactor's killer feature. Without it, NutriTrack's target is static even after 6 months of logging.
EFFORT
1 day
FIX
7700 kcal/kg formula + weekly trigger
15
Image storage on device
Camera captures saved to app-private dir. Never deleted.
IMPACT: Old food photos pile up. Forensic tools can recover. PII risk.
EFFORT
2 hours
FIX
Retention policy + cleanup cron
NutriTrack · Status Report · 2026-07-08
13 / 14

## Slide 14
WHAT TO DO NEXT
Three steps to get
NutriTrack shipping.
TODAY
Fix the build.
Run the 5-line edit list for RRect + Function() signatures. 45 minutes. Open the icon. Run flutter run.
THIS WEEK
Wire the data + add Sentry.
Replace 5 sample-data screens with real Drift. Add Sentry (2 hours). Wire 7 priority tests. ~3 days.
THIS MONTH
Ship differentiators.
Voice UI + camera verification + workout session + complete exercise DB. ~3 weeks. Then TestFlight + public beta.
Repo: github.com/albertlaudia/nutritrack · PB: pocketbase.scaleupcrm.com · 9,373 Dart LOC
NutriTrack · Status Report · 2026-07-08
14 / 14